## Action Plan
Action Plan Name: Formwork & Concrete Quality Plan
Template Description | This template is intended to be used as a guide for informational purposes only and not for the purpose of providing legal advice. It should be adapted to your company's best practices and project-specific requirements. You should contact your legal counsel to obtain advice with respect to any particular issue. Use of these materials does not guarantee compliance with applicable laws and regulations. This specific example demostates utilizing one singular inspection template across several Action Plan Items. As the internal party will be the singular party interacting with the checklist, consolidating the multiple tasks into one checklist eliminates the need for several unique checklist templates. To learn more about leveraging Action Plans, visit this Procore Support Article.
Number | Title | Acceptance Criteria | References | Due Dates (configurable on project) | Assignees | Verification Methods | Records | Blocking?
1 | CONCRETE PREPOUR CHECKS (PILE CAPS/BEAMS/ FOOTINGS/ SLAB ON GROUND/ LIFT PITS/ DETENTION TANKS) |  |  | -
1.1 | Internal Inspection | Complete section 1 of Formwork & Concrete Quality Checklist |  | - | Internal |  | Formwork & Concrete Quality Checklist
1.2 | Obtain Subcontractor ITP | Subcontractor to submit ITP |  | - | Subcontractor | Hold Point | Attachments Requested | Yes
1.3 | Geotech Engineering Sign-Off of Foundation Material | Determined by Geotech Engineer - Appropriate documentation to be provided by Engineer. |  | - | Third Party | Hold Point | Attachments Requested | Yes
2 | COLUMNS & INSITU WALLS
2.1 | Internal Inspection | Complete section 2 of Formwork & Concrete Quality Checklist |  | - | Internal |  | Formwork & Concrete Quality Checklist
2.2 | Obtain Subcontractor ITP | Subcontractor to submit ITP |  | - | Subcontractor | Hold Point | Attachments Requested | Yes
3 | FORMWORK
3.1 | Internal Inspection | Complete section 3 of Formwork & Concrete Quality Checklist |  | - | Internal |  | Formwork & Concrete Quality Checklist
3.2 | Formwork Design Received | Certified by Temp Works Engineer |  | - | Third Party | Hold Point | Attachments Requested | Yes
3.3 | Engage Independent Review (REMOVE IF NOT REQUIRED) | When transfer slab of 600mm or more an independent review of the formwork design has been received and reviewed. |  | - | Internal* (Rest of Plan) | Hold Point | Attachments Requested | Yes
3.4 | Back propping/Stripping procedure provided by temp works engineer | Certified by Temp Works Engineer |  | - | Third Party | Hold Point | Attachments Requested | Yes
3.5 | Engineer Formwork Inspection | Temp Works Engineer to Inspect prior to pouring concrete |  | - | Third Party | Hold Point | Attachments Requested | Yes
3.6 | Obtain Subcontractor ITP | Subcontractor to submit ITP |  | - | Subcontractor | Hold Point | Attachments Requested | Yes
4 | CORE SYSTEM
4.1 | Internal Inspection | Complete section 4 of Formwork & Concrete Quality Checklist |  | - | Internal |  | Formwork & Concrete Quality Checklist
4.2 | Obtain Subcontractor ITP | Subcontractor to submit ITP |  | - | Subcontractor | Hold Point | Attachments Requested | Yes
5 | REINFORCEMENT
5.1 | Internal Inspection | Complete section 5 of Formwork & Concrete Quality Checklist |  | - | Internal |  | Formwork & Concrete Quality Checklist
5.2 | Structural Engineer Inspection | Qualified engineer inspection per site specific requirement. Check all issues raised by engineer are completed and signed-off. Minimum inspection regime below – Pad footings/pile caps 100% Rafts 100% Critical structural elements as identified by structural engineer or certifying engineer 100% Core/shear walls – first of each type, each critical element, minimum 30% remaining at regular intervals Columns – first of each type, each critical column, minimum 30% remaining at regular intervals Slabs – 100% |  | - | Internal Third Party | Witness Point Hold Point | Attachments Requested | Yes
5.3 | Obtain Subcontractor ITP | Subcontractor to submit ITP |  | - | Subcontractor | Hold Point | Attachments Requested | Yes
6 | POST TENSIONING
6.1 | Internal Inspection | Complete section 6 of Formwork & Concrete Quality Checklist |  | - | Internal |  | Formwork & Concrete Quality Checklist
6.2 | PT Engineer Inspection | PT Engineer to Provide Inspection Report |  | - | Third Party | Hold Point | Attachments Requested | Yes
6.3 | Obtain Subcontractor ITP | Subcontractor to submit ITP |  | - | Subcontractor | Hold Point | Attachments Requested | Yes
7 | PENETRATIONS & CAST-INS
7.1 | Internal Inspection | Complete section 7 of Formwork & Concrete Quality Checklist |  | - | Internal |  | Formwork & Concrete Quality Checklist
7.2 | Obtain Subcontractor ITP | Subcontractor to submit ITP |  | - | Subcontractor Subcontractor Subcontractor Subcontractor | Hold Point Hold Point Hold Point Hold Point | Attachments Requested | Yes
8 | POST-POUR CHECKS
8.1 | Internal Inspection | Complete section 8 of Formwork & Concrete Quality Checklist |  | - | Internal |  | Formwork & Concrete Quality Checklist
8.2 | Formwork Engineer Approval | Written Approval to Strip & Backprop received from Formwork Engineer |  | - | Third Party | Hold Point | Attachments Requested | Yes
8.3 | Obtain Subcontractor ITP | Subcontractor to submit ITP |  | - | Subcontractor | Hold Point | Attachments Requested | Yes
8.4 | Obtain Tendon Extension Report | Subcontractor to submit final tendon extension report |  | - | Subcontractor | Hold Point | Attachments Requested | Yes
8.5 | Concrete Test Results | Subcontractor to submit concrete test results after allocated period |  | - | Subcontractor | Hold Point | Attachments Requested | Yes

## Inspection
Inspection Template Name: Formwork & Concrete Quality Checklist
Number | Title | Response
1 | Design Elements
1.1 | Concrete mix approved | [Procore] Yes/No
1.2 | Required MPA? | Text
1.3 | Required Finish/Class? | Text
1.4 | Waterproofing additive mixture/treatment? | Text
1.5 | Slump (mm)? | Text
1.6 | Curing Compound? | Text
1.7 | Formwork Type | Text
2 | Subcontractors, Suppliers, Consultant Details
2.1 | Subcontractors, Suppliers, Consultant Details | Text
2.2 | Geotech Engineer | Text
2.3 | Structural Engineer/s | Text
2.4 | Temp Works Engineer | Text
2.5 | Building Surveyor | Text
2.6 | Concrete S/C | Text
2.7 | Formwork S/C | Text
2.8 | Piling S/C | Text
3 | 1.0 CONCRETE PREPOUR CHECKS (PILE CAPS/BEAMS/ FOOTINGS/ SLAB ON GROUND/ LIFT PITS/ DETENTION TANKS)
3.1 | Check drawing No. & latest rev is being used by subcontractor | Pass / Fail / N/A
3.2 | Check blinding (per specifications) | Pass / Fail / N/A
3.3 | Check Termite Protection in place | Pass / Fail / N/A
3.4 | Check in-ground services installed under slab | Pass / Fail / N/A
3.5 | Check reinforcement of capping beam | Pass / Fail / N/A
3.6 | Check vapour barrier lapped/taped | Pass / Fail / N/A
3.7 | Check membrane requirements for pits (per specification) | Pass / Fail / N/A
3.8 | Cleaned & excess spoil removed | Pass / Fail / N/A
3.9 | Drawing/ Mud Map completed. Drawing/ mud-map prepared with applicable areas highlighted | Pass / Fail / N/A
3.10. | Geotech engineering sign off of foundation material. Check all issues raised by engineer are completed and signed-off | Pass / Fail / N/A
4 | 2.0 COLUMNS & INSITU WALLS
4.1 | Check drawing No. & latest rev is being used by subcontractor | Pass / Fail / N/A
4.2 | Set-out, plumb, rebates, recesses, etc | Pass / Fail / N/A
4.3 | Starter bars (cast in) & scabble | Pass / Fail / N/A
4.4 | Column formwork support system | Pass / Fail / N/A
4.5 | Shutters clean & clear of debris | Pass / Fail / N/A
5 | 3.0 FORMWORK
5.1 | Check drawing No. & latest rev is being used by subcontractor | Pass / Fail / N/A
5.2 | Formwork design received -certified by temp. works engineer | Pass / Fail / N/A
5.3 | Formwork installed per design including formwork components as per design, extension of screw jacks within specified limits, orientation and location of formwork components as per design. Check all issues raised by engineer are completed and signed-off | Pass / Fail / N/A
5.4 | Back propping/Stripping procedure provided by temp. works engineer | Pass / Fail / N/A
5.5 | Design allows adequate room for PT stressing | Pass / Fail / N/A
5.6 | Back propping to lower floors in place per engineer’s design | Pass / Fail / N/A
5.7 | Form face integrity (e.g. balcony class 2) | Pass / Fail / N/A
5.8 | Level, plumb, set downs, rebates, recesses, hobs | Pass / Fail / N/A
5.9 | Check edge rebates, blackouts, set downs, cast in items | Pass / Fail / N/A
5.1 | Drip Groove/Overflows | Pass / Fail / N/A
5.11 | Form face clear of debris | Pass / Fail / N/A
5.12 | Formwork installed as per design including formwork components as per design, extension of screw jacks within specified limits, orientation and location of formwork components as per design | Pass / Fail / N/A
5.13 | Formwork inspected by temp. works engineer prior to pouring concrete | Pass / Fail / N/A
6 | 4.0 CORE SYSTEM
6.1 | Check drawing No. & latest rev is being used by subcontractor | Pass / Fail / N/A
6.2 | Design available and certified by structural engineer | Pass / Fail / N/A
6.3 | Check shutter verticality as-built from previous level provided and corrections made | Pass / Fail / N/A
6.4 | Check services penetrations installed | Pass / Fail / N/A
6.5 | Check vertical & horizontal Reinforcement | Pass / Fail / N/A
6.6 | Check header Beams & Additional Bars | Pass / Fail / N/A
6.7 | Check door support beams | Pass / Fail / N/A
6.8 | Check external & Internal Shutters (Z ties) | Pass / Fail / N/A
6.9 | Check starter bars for horizontal elements | Pass / Fail / N/A
6.10. | Check lift Unistrut's & call buttons | Pass / Fail / N/A
6.11. | Check protection decks, working platforms, winch beams installed | Pass / Fail / N/A
7 | 5.0 REINFORCEMENT
7 | Check drawing No. & latest rev is being used by subcontractor | Pass / Fail / N/A
7.1 | Reinforcement installation per design | Pass / Fail / N/A
7.2 | Lap lengths | Pass / Fail / N/A
7.3 | Cover | Pass / Fail / N/A
7.4 | Chairs/Supports (plastic where required) | Pass / Fail / N/A
7.5 | Qualified engineer inspection per site specific requirement. Check all issues raised by engineer are completed and signed-off. Minimum inspection regime below – Pad footings/pile caps 100% Rafts 100% Critical structural elements as identified by structural engineer or certifying engineer 100% Core/shear walls – first of each type, each critical element, minimum 30% remaining at regular intervals Columns – first of each type, each critical column, minimum 30% remaining at regular intervals Slabs – 100%. Check all issues raised by engineer are completed and signed-off | Pass / Fail / N/A
7.6 | Photographic record of completed reinforcement prior to placing concrete | Pass / Fail / N/A
8 | 6.0 POST TENSIONING
8.1 | Installation as per design | Pass / Fail / N/A
8.2 | Stressing Final complete (attach Tendon extension report). Submit to PT engineer for approval | Pass / Fail / N/A
8.3 | PT Engineer’ s inspection completed. Check all issues raised by engineer are completed and signed-off | Pass / Fail / N/A
9 | 7.0 PENETRATIONS
9.1 | Located as per design | Pass / Fail / N/A
9.2 | Hydraulics | Pass / Fail / N/A
9.3 | Mechanical | Pass / Fail / N/A
9.4 | Electrical | Pass / Fail / N/A
9.5 | Sprinkler/Fire | Pass / Fail / N/A
9.6 | Bin Chute (cast in supplied) | Pass / Fail / N/A
9.7 | Miscellaneous Cast in items - List | Text
10 | 8.0 POST-POUR CHECKS
10.1 | Concrete curing completed | Pass / Fail / N/A
10.2 | PT grouting completed | Pass / Fail / N/A
10.3 | As built survey to check levels/set downs/penos are within tolerance | Pass / Fail / N/A
10.4 | Concrete test reports verify design concrete strength